## Sheet1
System Area | System Area | Problem | Action | Pain | NOTES | Followup - Pat
Expense Setup | Expense Type: CAM, Real Estate Taxes, and Insurance | Expense schedules that go beyond the payment end date of the contract | Delete CAM setups for future years, and change current year setup to be the payment end date of contract. Pmt end date = 6/31/18 | Currently they have to delete all setups by hand, or will have to edit current year and all future years for every change | Logged into support SUPPORT-1007 | Responded to Shelley - she has the info available in the Train environment and to test there; then push to Prod
Contact Management |  |  | Need to be able to mass update Contacts via project membership tool |  | Logged into IWMS-14550 | Shelbii closed as unable to reproduce; Louise reopened case today and reassigned back to Shelbii to vet
Wizard |  | How to setup a Covenant template and a Responsibilities template | Create a contract named "Wizard - X" and then add responsibilities and covenants to it. Select appropriate template going forward when using the wizard | Very painful when abstracting | Discussed via webex. Follow-up to make sure they were able to do it ok | 8/26/2013 Shelley said she was able to do and using that and Mike Kim did some work for her
Insurance |  | Ability to upload into insurance from Excel | Louise to get spreadsheet template and test it, then provide to Academy |  | Have the spreadsheet from IWMS-14350. Need Pat to test it and work with Shelley. Show them how to upload (provide examples) | The insurance spreadsheet (which is available in 9.2.2.1 only) throws errors - Gowri reviewing
Excel Uploads |  |  | Provide me a list of the areas need to upload to | Store open/close dates (move in date), close date, year open, | Remind Shelley to get us a list of the data she wants to upload in addition to the other ones mentioned here. | 8/28 - talked with Shelley re: this - she said she couldn’t remember whether she sent it or not but would run the report to see what was missing and would respond back.
Document Uploading |  | Initial loading of documents | Louise/Pat to show Academy how to use WebDav for drag and drop |  | Show them how to use WebDav | 8/26 - I will send Shelley a link to AnyClient (she has Windows XP) and we'll set up a webex 9/5 - WebDav Training completed
Space Uploads |  | Have data to upload into space | Training session for Space spreadsheet |  | Show them how to upload (provide examples) | scheduling Training Webex w/o 9/9
Facility Uploads |  | Have data to add into facility | Training session for Facilities spreadsheet |  | Show them how to upload (provide examples) | scheduling Training Webex w/o 9/9
Rentable Area |  | Have to update rentable area on the facility and contracts separately | Academy is going to provide some examples | Having to enter/update in multiple places | Emailed Ken to see if it SHOULD be this way | asked Louise whether she obtained response from Ken
Center Uploads |  |  | Training session for Center Uploads |  | Show them how to upload (provide examples) | ?? Need clarification on this - asked Louise
Approvals |  | Vendor showing Dates | Possible bug - Louise to report and follow up |  | Report back that this was by design because of the vendor begin end dates. I think we should put the vendor name first, then follow with the dates. Enter as enhancment request | Need clarification on this -
Location Uploads |  |  | Training session for Location uploads |  | Show them how to upload (provide examples) | ??? We can't upload "locations" via spreadsheet - need clarification